## Test Plan
Proper Place — Pre-Release Test Plan (v2.2.0)
Tester: Pierce Shapton ¦ Platforms: iOS, Android, Web ¦ Date: _______________
Test # | Day | Section | Test Description | Priority | Result | Notes
DAY 1 — CORE USER FLOWS & PAYMENTS
1. AUTHENTICATION
1.1 Fresh Install & Welcome
1.1.1 | 1 | Authentication | App opens to Welcome Screen with background image and branding | Important
1.1.2 | 1 | Authentication | "Login" button navigates to Login Screen | Blocker
1.1.3 | 1 | Authentication | "Sign Up" button navigates to Signup Screen | Blocker
1.1.4 | 1 | Authentication | App branding/logo displays correctly (no broken images) | Important
1.2 Sign Up
1.2.1 | 1 | Authentication | Enter valid name, email, password, confirm password | Blocker
1.2.2 | 1 | Authentication | Vehicle registration field accepts valid UK plates (e.g. AB12 CDE) | Important
1.2.3 | 1 | Authentication | Vehicle dimension sliders work (height/width/length) and save | Important
1.2.4 | 1 | Authentication | Password mismatch shows warning message | Blocker
1.2.5 | 1 | Authentication | Password visibility toggle (show/hide) works on both fields | Nice-to-have
1.2.6 | 1 | Authentication | Weak password (less than 6 chars) shows error | Blocker
1.2.7 | 1 | Authentication | Duplicate email shows appropriate error | Blocker
1.2.8 | 1 | Authentication | Empty required fields show validation errors | Blocker
1.2.9 | 1 | Authentication | Successful signup navigates to Email Verification Screen | Blocker
1.2.10 | 1 | Authentication | Rate limiting: 6th signup attempt within an hour is blocked | Important
1.3 Email Verification
1.3.1 | 1 | Authentication | Email Verification Screen displays with correct email address | Blocker
1.3.2 | 1 | Authentication | Verification email arrives in inbox (check spam) | Blocker |  | ⚠️ SMTP may not be working in production yet
1.3.3 | 1 | Authentication | Clicking verification link in email marks user as verified | Blocker
1.3.4 | 1 | Authentication | App auto-detects verification (polls every 5s) and proceeds to home | Blocker
1.3.5 | 1 | Authentication | "Resend" button sends a new verification email | Important
1.3.6 | 1 | Authentication | Back button returns to Welcome Screen | Important
1.3.7 | 1 | Authentication | Logging in with unverified account shows verification screen | Blocker
1.4 Login
1.4.1 | 1 | Authentication | Valid email + password logs in successfully | Blocker
1.4.2 | 1 | Authentication | Invalid password shows error message | Blocker
1.4.3 | 1 | Authentication | Non-existent email shows error (shouldn't reveal if account exists) | Blocker
1.4.4 | 1 | Authentication | "Remember Me" checkbox persists login across app restart | Important
1.4.5 | 1 | Authentication | Password visibility toggle works | Nice-to-have
1.4.6 | 1 | Authentication | Rate limiting: 6th login attempt within 15 mins is blocked | Important
1.5 Forgot Password
1.5.1 | 1 | Authentication | "Forgot Password" link from login screen works | Blocker
1.5.2 | 1 | Authentication | Entering valid email shows success message | Blocker
1.5.3 | 1 | Authentication | Reset email arrives with valid link | Blocker |  | ⚠️ Depends on SMTP fix
1.5.4 | 1 | Authentication | Reset link opens password reset form | Blocker
1.5.5 | 1 | Authentication | Setting new password works and allows login | Blocker
1.5.6 | 1 | Authentication | Entering non-existent email still shows success (no info leak) | Important
1.6 Session Management
1.6.1 | 1 | Authentication | Token auto-refreshes (stay logged in for 30+ mins without action) | Blocker
1.6.2 | 1 | Authentication | Logout clears session and returns to Welcome Screen | Blocker
1.6.3 | 1 | Authentication | After logout, pressing back doesn't return to authenticated screens | Important
1.6.4 | 1 | Authentication | Force-closing and reopening app maintains session (if Remember Me) | Important
2. MAP & BROWSING
2.1 Map Display
2.1.1 | 1 | Map & Browsing | Map loads with Google Maps tiles | Blocker
2.1.2 | 1 | Map & Browsing | Current location button works (if permissions granted) | Important
2.1.3 | 1 | Map & Browsing | Custom "P" pin markers appear when zoomed in (zoom 11+) | Blocker
2.1.4 | 1 | Map & Browsing | Markers disappear when zoomed out too far | Nice-to-have
2.1.5 | 1 | Map & Browsing | Pin tip points at the exact location (not offset) | Important
2.1.6 | 1 | Map & Browsing | Map type toggle works (satellite/standard) | Nice-to-have
2.1.7 | 1 | Map & Browsing | Map remembers last position between sessions | Nice-to-have
2.2 Place Discovery
2.2.1 | 1 | Map & Browsing | Tapping a marker shows place preview card | Blocker
2.2.2 | 1 | Map & Browsing | Place preview shows: name, price, image thumbnail | Blocker
2.2.3 | 1 | Map & Browsing | Tapping preview navigates to Place Detail Screen | Blocker
2.2.4 | 1 | Map & Browsing | Facility filter buttons appear and are functional | Important
2.2.5 | 1 | Map & Browsing | Filtering by facility updates visible markers | Important
2.2.6 | 1 | Map & Browsing | Search functionality finds places by name/location | Important
2.2.7 | 1 | Map & Browsing | Vehicle size filter toggle filters out places too small for your van | Important
2.3 Route Planning
2.3.1 | 1 | Map & Browsing | Route planning (start/destination) draws a route on map | Important
2.3.2 | 1 | Map & Browsing | Search radius circle displays around destination | Nice-to-have
2.4 Offline Maps
2.4.1 | 1 | Map & Browsing | Offline regions screen lists all 16 UK regions | Important
2.4.2 | 1 | Map & Browsing | Downloading a region shows progress indicator | Important
2.4.3 | 1 | Map & Browsing | Downloaded region data persists when offline | Important
2.4.4 | 1 | Map & Browsing | Cache size displays correctly | Nice-to-have
3. PLACE DETAIL
3.1 | 1 | Place Detail | Place Detail Screen loads with all information | Blocker
3.2 | 1 | Place Detail | Image carousel swipes between photos | Blocker
3.3 | 1 | Place Detail | Place name, description, address display correctly | Blocker
3.4 | 1 | Place Detail | Price per night displays correctly (£) | Blocker
3.5 | 1 | Place Detail | Amenities list shows correct icons | Important
3.6 | 1 | Place Detail | Reviews section shows existing reviews with star ratings | Important
3.7 | 1 | Place Detail | Average rating calculates correctly | Important
3.8 | 1 | Place Detail | Review photos display in reviews | Nice-to-have
3.9 | 1 | Place Detail | Availability calendar shows booked dates in green | Blocker
3.10 | 1 | Place Detail | Vehicle fit warning appears if van is too large | Important
3.11 | 1 | Place Detail | Business description, food menu, access route show if available | Nice-to-have
3.12 | 1 | Place Detail | Host info (name) displays | Important
3.13 | 1 | Place Detail | "Add to Favourites" heart icon works | Important
3.14 | 1 | Place Detail | Place is marked as favourite and appears in Favourites screen | Important
4. BOOKING FLOW & PAYMENTS
4.1 Creating a Booking
4.1.1 | 1 | Booking & Payment | "Book Now" button opens booking calendar | Blocker
4.1.2 | 1 | Booking & Payment | Select check-in date on calendar (orange highlight) | Blocker
4.1.3 | 1 | Booking & Payment | Select check-out date (range highlighted) | Blocker
4.1.4 | 1 | Booking & Payment | Cannot select dates that are already booked (green) | Blocker
4.1.5 | 1 | Booking & Payment | Cannot select past dates | Blocker
4.1.6 | 1 | Booking & Payment | Check-in/check-out times can be adjusted | Important
4.1.7 | 1 | Booking & Payment | Early arrival fee (£5/hr before standard time) calculates | Important
4.1.8 | 1 | Booking & Payment | Late departure fee (£5/hr after standard time) calculates | Important
4.1.9 | 1 | Booking & Payment | Total price displays correctly (nights × price + any fees) | Blocker
4.1.10 | 1 | Booking & Payment | Van registration is pre-filled from profile or can be entered | Important
4.1.11 | 1 | Booking & Payment | UK number plate validation works (rejects invalid formats) | Important
4.1.12 | 1 | Booking & Payment | Capacity check: booking rejected if place is full | Blocker
4.2 Stripe Payment — Test Cards: 4242424242424242 (success), 4000000000000002 (decline), 4000002500003155 (3DS)
4.2.1 | 1 | Booking & Payment | Stripe payment sheet appears after confirming booking details | Blocker
4.2.2 | 1 | Booking & Payment | Successful payment with test card 4242... creates booking | Blocker
4.2.3 | 1 | Booking & Payment | Booking status shows as "Pending" (awaiting host approval) | Blocker
4.2.4 | 1 | Booking & Payment | Declined card (4000...0002) shows appropriate error message | Blocker
4.2.5 | 1 | Booking & Payment | 3D Secure card (4000...3155) shows authentication challenge | Important
4.2.6 | 1 | Booking & Payment | Payment amount matches displayed total | Blocker
4.2.7 | 1 | Booking & Payment | Funds are HELD (not captured) — check Stripe Dashboard | Blocker
4.2.8 | 1 | Booking & Payment | Booking confirmation screen displays after successful payment | Blocker
4.2.9 | 1 | Booking & Payment | Booking reference number generated (PP-YYMMDD-XXXX format) | Important
4.3 Booking Management (Guest)
4.3.1 | 1 | Booking & Payment | New booking appears in "My Bookings" screen | Blocker
4.3.2 | 1 | Booking & Payment | Booking tabs filter correctly (All/Pending/Confirmed/Completed) | Important
4.3.3 | 1 | Booking & Payment | Calendar view toggle shows bookings on calendar | Important
4.3.4 | 1 | Booking & Payment | Search within bookings works | Nice-to-have
4.3.5 | 1 | Booking & Payment | Tapping a booking opens Booking Detail Screen | Blocker
4.3.6 | 1 | Booking & Payment | Booking detail shows: dates, place, status, total paid | Blocker
4.3.7 | 1 | Booking & Payment | "Get Directions" button opens Waze/Maps | Important
4.3.8 | 1 | Booking & Payment | "Chat with Host" button opens messaging | Blocker
4.3.9 | 1 | Booking & Payment | Cancel booking releases the payment hold | Blocker
4.3.10 | 1 | Booking & Payment | Cancelled booking status updates correctly | Blocker
5. MESSAGING SYSTEM
5.1 Guest → Host Chat
5.1.1 | 1 | Messaging | Opening chat from booking shows conversation | Blocker
5.1.2 | 1 | Messaging | Sending a text message works | Blocker
5.1.3 | 1 | Messaging | Messages appear in correct order (newest at bottom) | Blocker
5.1.4 | 1 | Messaging | Message polling (3s) picks up new messages from host | Blocker
5.1.5 | 1 | Messaging | Unread message badge shows on Bookings/Messages tab | Blocker
5.1.6 | 1 | Messaging | Badge count clears when conversation is opened | Important
5.1.7 | 1 | Messaging | All Chats screen lists all conversations | Blocker
5.1.8 | 1 | Messaging | Swipe actions: mark unread, delete work | Nice-to-have
5.2 Chat Lifecycle
5.2.1 | 1 | Messaging | Chat is "open" during active booking | Important
5.2.2 | 1 | Messaging | Chat shows "closing soon" near end of stay | Important
5.2.3 | 1 | Messaging | Chat closes after booking completion | Important
5.2.4 | 1 | Messaging | "Request Reopen" button available on closed chats | Important
5.2.5 | 1 | Messaging | Host can approve/deny reopen request | Important
5.3.1 | 1 | Messaging | Host response time label displays (e.g. "Usually responds within 1 hour") | Nice-to-have
6. REVIEWS
6.1 | 1 | Reviews | After a completed booking, "Leave Review" option appears | Blocker
6.2 | 1 | Reviews | Star rating selector works (1-5 stars) | Blocker
6.3 | 1 | Reviews | Text comment field accepts input | Blocker
6.4 | 1 | Reviews | Photo upload (up to 5 photos) works | Important
6.5 | 1 | Reviews | EXIF metadata stripped from photos (privacy) | Important |  | Upload photo with GPS, verify stripped
6.6 | 1 | Reviews | Submitting review succeeds | Blocker
6.7 | 1 | Reviews | Review appears on the place's detail page | Blocker
6.8 | 1 | Reviews | Average rating updates after new review | Important
7. FAVOURITES
7.1 | 1 | Favourites | Adding a place to favourites from detail screen works | Important
7.2 | 1 | Favourites | Favourites tab shows all saved places | Important
7.3 | 1 | Favourites | Removing a favourite updates the list | Important
7.4 | 1 | Favourites | Favourite heart markers appear on map | Nice-to-have
7.5 | 1 | Favourites | Search/filter within favourites works | Nice-to-have
DAY 2 — HOST, ADMIN, WEBSITE & EDGE CASES
8. HOST APPLICATION & ONBOARDING
8.1 Become a Host
8.1.1 | 2 | Host Onboarding | "Become a Host" option in More menu visible for regular users | Blocker
8.1.2 | 2 | Host Onboarding | Host application form loads with all fields | Blocker
8.1.3 | 2 | Host Onboarding | Contact name, email, phone fields work | Blocker
8.1.4 | 2 | Host Onboarding | Business description field works | Important
8.1.5 | 2 | Host Onboarding | Address field uses Google Places autocomplete | Blocker
8.1.6 | 2 | Host Onboarding | Business type selector works (pub, farm, etc.) | Important
8.1.7 | 2 | Host Onboarding | Number of van spaces field works | Important
8.1.8 | 2 | Host Onboarding | Referral code field works (optional) | Nice-to-have
8.1.9 | 2 | Host Onboarding | GPS location auto-populates from address | Important
8.1.10 | 2 | Host Onboarding | Submitting application shows success message | Blocker
8.2 Host Contract
8.2.1 | 2 | Host Onboarding | After application approval, Host Contract screen appears | Blocker
8.2.2 | 2 | Host Onboarding | Contract text is readable and scrollable | Blocker
8.2.3 | 2 | Host Onboarding | Must scroll to bottom before "Accept" becomes enabled | Blocker
8.2.4 | 2 | Host Onboarding | Accepting contract records acceptance (IP, timestamp) | Blocker
8.2.5 | 2 | Host Onboarding | After contract, Stripe Payout Setup screen appears | Blocker
8.3 Stripe Connect (Host Payouts)
8.3.1 | 2 | Host Onboarding | Stripe Connect onboarding opens external browser | Blocker
8.3.2 | 2 | Host Onboarding | Completing Stripe onboarding returns to app | Blocker
8.3.3 | 2 | Host Onboarding | App verifies Stripe Connect status on return | Blocker
8.3.4 | 2 | Host Onboarding | If onboarding incomplete, shows "Complete Setup" option | Important
8.3.5 | 2 | Host Onboarding | Payout status visible on Host Dashboard | Important
9. HOST SITE MANAGEMENT
9.1 Create a Site
9.1.1 | 2 | Host Sites | "Create Site" button available in Host mode | Blocker
9.1.2 | 2 | Host Sites | All form fields work: name, address, description | Blocker
9.1.3 | 2 | Host Sites | Access route description field works | Important
9.1.4 | 2 | Host Sites | Price per night field (numeric input) works | Blocker
9.1.5 | 2 | Host Sites | Website URL field works | Nice-to-have
9.1.6 | 2 | Host Sites | Business name and description fields work | Important
9.1.7 | 2 | Host Sites | Food menu description field works | Nice-to-have
9.1.8 | 2 | Host Sites | Main photo upload works | Blocker
9.1.9 | 2 | Host Sites | Supporting photos upload (multiple) works | Important
9.1.10 | 2 | Host Sites | Business photos upload works | Nice-to-have
9.1.11 | 2 | Host Sites | Vehicle dimension limits with metric/imperial toggle | Important
9.1.12 | 2 | Host Sites | Number of van spaces field works | Blocker
9.1.13 | 2 | Host Sites | Google Maps pin placement for exact location | Blocker
9.1.14 | 2 | Host Sites | Saving site shows success and appears in "My Sites" | Blocker
9.1.15 | 2 | Host Sites | New site status is "Pending" (awaiting admin approval) | Blocker
9.2 Edit a Site
9.2.1 | 2 | Host Sites | Tapping a site opens it for editing | Blocker
9.2.2 | 2 | Host Sites | All fields are pre-populated with existing data | Blocker
9.2.3 | 2 | Host Sites | Changes save correctly | Blocker
9.2.4 | 2 | Host Sites | Adding/removing photos works | Important
9.3 My Sites List
9.3.1 | 2 | Host Sites | Sites list shows all host's sites | Blocker
9.3.2 | 2 | Host Sites | Status badges display correctly (Drafting/Pending/Approved/Rejected) | Blocker
9.3.3 | 2 | Host Sites | Only approved sites appear on the public map | Blocker
9.3.4 | 2 | Host Sites | Mark site as unavailable toggles it off the map | Important
9.3.5 | 2 | Host Sites | Mark site as available restores it | Important
10. HOST BOOKING MANAGEMENT
10.1 | 2 | Host Bookings | Host sees incoming bookings in Host Bookings screen | Blocker
10.2 | 2 | Host Bookings | Booking shows guest info, dates, van details | Blocker
10.3 | 2 | Host Bookings | "Approve" button captures the held payment (check Stripe) | Blocker
10.4 | 2 | Host Bookings | After approval, booking status changes to "Confirmed" | Blocker
10.5 | 2 | Host Bookings | "Reject" button cancels the payment hold (check Stripe) | Blocker
10.6 | 2 | Host Bookings | After rejection, booking status changes to "Rejected" | Blocker
10.7 | 2 | Host Bookings | Calendar view shows bookings on dates | Important
10.8 | 2 | Host Bookings | Filter tabs work (Confirmed/Pending/Completed/All) | Important
10.9 | 2 | Host Bookings | Unread message badges appear per booking | Important
10.10 | 2 | Host Bookings | 15% platform fee deducted from host payout (check Stripe) | Blocker
11. HOST DASHBOARD & FEATURES
11.1 | 2 | Host Dashboard | Dashboard shows: unread messages, total bookings, revenue | Blocker
11.2 | 2 | Host Dashboard | Pending payments count is accurate | Important
11.3 | 2 | Host Dashboard | Average length of stay calculates | Nice-to-have
11.4 | 2 | Host Dashboard | Recent conversations list is clickable | Important
11.5 | 2 | Host Dashboard | Recent bookings list is clickable | Important
11.1 Auto-Messages
11.1.1 | 2 | Host Dashboard | Auto-message config screen accessible per place | Important
11.1.2 | 2 | Host Dashboard | Can set message for "On Booking" trigger | Important
11.1.3 | 2 | Host Dashboard | Can set message for "24h Before Check-in" trigger | Important
11.1.4 | 2 | Host Dashboard | Can set message for "1h Before Arrival" trigger | Important
11.1.5 | 2 | Host Dashboard | Can set message for "At Checkout" trigger | Important
11.1.6 | 2 | Host Dashboard | Auto-message actually sends at the correct trigger time | Important |  | Hard to test — check DB or wait
11.2 Host Reviews & Chat
11.2.1 | 2 | Host Dashboard | Host Reviews screen shows all reviews across all places | Important
11.2.2 | 2 | Host Dashboard | Filter by star rating works | Nice-to-have
11.2.3 | 2 | Host Dashboard | Review photos display correctly | Nice-to-have
11.3.1 | 2 | Host Dashboard | Host chat screen lists all guest conversations | Blocker
11.3.2 | 2 | Host Dashboard | Open/closed sections display correctly | Important
11.3.3 | 2 | Host Dashboard | Sending messages to guests works | Blocker
11.3.4 | 2 | Host Dashboard | Reopen request handling works (approve/deny) | Important
11.4.1 | 2 | Host Dashboard | Host can rate a guest after completed booking | Important
11.4.2 | 2 | Host Dashboard | Guest rating is stored and retrievable | Important
12. ADMIN PANEL — Login: admin@properplace.com / AdminPass123!
12.1.1 | 2 | Admin Panel | Admin Dashboard loads with quick-action cards | Blocker
12.1.2 | 2 | Admin Panel | Booking search works | Important
12.2.1 | 2 | Admin Panel | Pending/Approved/Rejected tabs show correct counts | Blocker
12.2.2 | 2 | Admin Panel | Tapping a pending place shows full detail with images | Blocker
12.2.3 | 2 | Admin Panel | Host info displayed (total sites, join date, contract status) | Important
12.2.4 | 2 | Admin Panel | Google Maps preview shows place location | Important
12.2.5 | 2 | Admin Panel | "Approve" button approves and place appears on map | Blocker
12.2.6 | 2 | Admin Panel | "Reject" button rejects with reason | Blocker
12.2.7 | 2 | Admin Panel | "Remove" button removes an approved place | Important
12.3.1 | 2 | Admin Panel | All platform bookings are visible | Blocker
12.3.2 | 2 | Admin Panel | Filter by status works (All/Pending/Confirmed/Completed/Cancelled) | Important
12.4.1 | 2 | Admin Panel | Admin can view all conversations | Important
12.4.2 | 2 | Admin Panel | Admin can send messages | Important
12.5.1 | 2 | Admin Panel | Contact submissions appear with status (new/read/responded/closed) | Blocker
12.5.2 | 2 | Admin Panel | Filter by status works | Important
12.5.3 | 2 | Admin Panel | Filter by category (hosts/users) works | Important
12.5.4 | 2 | Admin Panel | Can update contact status | Important
13. PROFILE & SETTINGS
13.1 | 2 | Profile | Profile screen shows current name, email, phone, bio | Blocker
13.2 | 2 | Profile | Editing name saves correctly | Blocker
13.3 | 2 | Profile | Editing phone number saves correctly | Important
13.4 | 2 | Profile | Editing bio saves correctly | Nice-to-have
13.5 | 2 | Profile | Vehicle registration can be updated | Important
13.6 | 2 | Profile | Vehicle dimensions screen works (ft/m toggle, sliders) | Important
13.7 | 2 | Profile | "Contact Us" form accessible and submits | Important
13.8 | 2 | Profile | T&C and Privacy links open correctly | Important
13.9 | 2 | Profile | Logout works from More menu | Blocker
14. PUSH NOTIFICATIONS
14.1 | 2 | Notifications | App requests notification permission on first launch | Important
14.2 | 2 | Notifications | Device token registered with backend | Important
14.3 | 2 | Notifications | Push notification received for new booking (as host) | Important
14.4 | 2 | Notifications | Push notification received for new message | Important
14.5 | 2 | Notifications | Tapping notification opens relevant screen | Important
14.6 | 2 | Notifications | Badge counts update on bottom nav bar | Blocker
14.7 | 2 | Notifications | Device token unregistered on logout | Nice-to-have
15. WEBSITE (proper-place.co.uk)
15.1 Public Pages
15.1.1 | 2 | Website | Homepage loads with hero, featured places, how-it-works | Blocker
15.1.2 | 2 | Website | Navigation bar links all work | Blocker
15.1.3 | 2 | Website | Footer links all work | Important
15.1.4 | 2 | Website | Cookie consent banner appears and works | Blocker
15.1.5 | 2 | Website | /browse — Google Maps loads with place markers | Blocker
15.1.6 | 2 | Website | /browse — Clicking marker shows place card | Blocker
15.1.7 | 2 | Website | /place/[id] — Place detail page loads with images, amenities, reviews | Blocker
15.1.8 | 2 | Website | /about — About page loads | Important
15.1.9 | 2 | Website | /how-it-works — Page loads with steps for guests and hosts | Important
15.1.10 | 2 | Website | /download — App download page with store buttons | Important
15.1.11 | 2 | Website | /contact — Contact form submits successfully | Blocker
15.1.12 | 2 | Website | /privacy — Privacy policy loads | Blocker
15.1.13 | 2 | Website | /terms — Terms of service loads | Blocker
15.1.14 | 2 | Website | /cookies — Cookie policy loads | Important
15.1.15 | 2 | Website | /scan — QR code landing page loads | Nice-to-have
15.1.16 | 2 | Website | /become-host — Host recruitment page loads | Important
15.1.17 | 2 | Website | /host-signup — Host lead form submits | Important
15.1.18 | 2 | Website | /qr-codes — QR code generator works, PNG download works | Nice-to-have
15.2 Website Auth
15.2.1 | 2 | Website | /auth/signup — Registration works with all fields | Blocker
15.2.2 | 2 | Website | Referral code field on signup works | Important
15.2.3 | 2 | Website | /auth/login — Login works | Blocker
15.2.4 | 2 | Website | Forgot password flow works from login page | Blocker
15.2.5 | 2 | Website | Token auto-refresh works (stay logged in) | Important
15.3 Website Booking Flow
15.3.1 | 2 | Website | /place/[id]/book — Booking form loads | Blocker
15.3.2 | 2 | Website | Date picker works with unavailable dates blocked | Blocker
15.3.3 | 2 | Website | Vehicle registration and phone fields work | Important
15.3.4 | 2 | Website | Vehicle dimensions can be entered | Important
15.3.5 | 2 | Website | Price calculation displays correctly | Blocker
15.3.6 | 2 | Website | Stripe payment works (test card) | Blocker
15.3.7 | 2 | Website | Booking success confirmation shows | Blocker
15.4 Website Dashboard
15.4.1 | 2 | Website | /dashboard — Overview loads with role-based content | Blocker
15.4.2 | 2 | Website | /dashboard/bookings — Guest bookings list with filters | Blocker
15.4.3 | 2 | Website | /dashboard/bookings/[id] — Booking detail, cancel, review | Blocker
15.4.4 | 2 | Website | /dashboard/messages — Conversations list | Blocker
15.4.5 | 2 | Website | /dashboard/messages/[userId] — Chat works with polling | Blocker
15.4.6 | 2 | Website | /dashboard/profile — Profile, Vehicle, Security tabs | Important
15.4.7 | 2 | Website | /dashboard/referrals — Referral code, stats, share | Important
15.4.8 | 2 | Website | /dashboard/places — Host places list (if host) | Important
15.4.9 | 2 | Website | /dashboard/places/new — Create place form | Important
15.4.10 | 2 | Website | /dashboard/host/bookings — Host booking management | Important
15.4.11 | 2 | Website | /dashboard/host/auto-messages — Auto-message config | Important
15.5 Website Admin
15.5.1 | 2 | Website | /dashboard/admin — Admin stats display | Blocker
15.5.2 | 2 | Website | /dashboard/admin/users — User management, role changes | Important
15.5.3 | 2 | Website | /dashboard/admin/places — Place approvals | Blocker
15.5.4 | 2 | Website | /dashboard/admin/bookings — All bookings search | Important
15.5.5 | 2 | Website | /dashboard/admin/contacts — Support ticket management | Important
15.6 Mobile Responsiveness
15.6.1 | 2 | Website | Homepage looks correct on mobile (Chrome DevTools) | Blocker
15.6.2 | 2 | Website | Navigation hamburger menu works on mobile | Blocker
15.6.3 | 2 | Website | Browse map is usable on mobile | Important
15.6.4 | 2 | Website | Booking form works on mobile | Blocker
15.6.5 | 2 | Website | Dashboard sidebar collapses on mobile | Important
16. END-TO-END FLOW TEST (MOST IMPORTANT)
16.1 | 2 | E2E Flow | Create new guest account (app) | Blocker
16.2 | 2 | E2E Flow | Verify email | Blocker
16.3 | 2 | E2E Flow | Set vehicle dimensions | Important
16.4 | 2 | E2E Flow | Browse map and find a place | Blocker
16.5 | 2 | E2E Flow | View place detail, check amenities and reviews | Blocker
16.6 | 2 | E2E Flow | Add place to favourites | Important
16.7 | 2 | E2E Flow | Start booking: select dates | Blocker
16.8 | 2 | E2E Flow | Complete Stripe payment (test card 4242...) | Blocker
16.9 | 2 | E2E Flow | Verify booking appears as "Pending" | Blocker
16.10 | 2 | E2E Flow | Send message to host via booking chat | Blocker
16.11 | 2 | E2E Flow | SWITCH TO HOST ACCOUNT | Blocker
16.12 | 2 | E2E Flow | Host sees pending booking in dashboard | Blocker
16.13 | 2 | E2E Flow | Host sees guest message | Blocker
16.14 | 2 | E2E Flow | Host replies to message | Blocker
16.15 | 2 | E2E Flow | Host approves booking | Blocker
16.16 | 2 | E2E Flow | Verify Stripe: payment captured, 15% fee taken | Blocker |  | Check Stripe Dashboard
16.17 | 2 | E2E Flow | SWITCH TO GUEST ACCOUNT | Blocker
16.18 | 2 | E2E Flow | Guest sees booking status changed to "Confirmed" | Blocker
16.19 | 2 | E2E Flow | Guest sees host's reply message | Blocker
16.20 | 2 | E2E Flow | Guest gets directions via Waze/Maps | Important
16.21 | 2 | E2E Flow | After stay: guest leaves a review (stars + text + photo) | Blocker
16.22 | 2 | E2E Flow | SWITCH TO HOST ACCOUNT | Blocker
16.23 | 2 | E2E Flow | Host sees the review | Blocker
16.24 | 2 | E2E Flow | Host rates the guest | Important
16.25 | 2 | E2E Flow | SWITCH TO ADMIN ACCOUNT | Blocker
16.26 | 2 | E2E Flow | Admin sees the booking in "All Bookings" | Blocker
16.27 | 2 | E2E Flow | Admin sees the review | Important
16.28 | 2 | E2E Flow | Guest makes another booking (same or different place) | Blocker
16.29 | 2 | E2E Flow | Host rejects it | Blocker
16.30 | 2 | E2E Flow | Guest sees status "Rejected" | Blocker
16.31 | 2 | E2E Flow | Verify Stripe: payment hold released/refunded | Blocker |  | Check Stripe Dashboard
16.32 | 2 | E2E Flow | Guest makes a booking and pays | Blocker
16.33 | 2 | E2E Flow | Guest cancels the booking | Blocker
16.34 | 2 | E2E Flow | Verify Stripe: payment hold released | Blocker
16.35 | 2 | E2E Flow | Booking shows as "Cancelled" | Blocker
17. HOST SITE SUBMISSION → APPROVAL FLOW
17.1 | 2 | Site Approval | Host creates a new site with all details + photos | Blocker
17.2 | 2 | Site Approval | Site shows as "Pending" in host's My Sites | Blocker
17.3 | 2 | Site Approval | LOGIN AS ADMIN | Blocker
17.4 | 2 | Site Approval | Site appears in admin Place Approvals → Pending tab | Blocker
17.5 | 2 | Site Approval | Admin reviews all details (images, host info, map) | Blocker
17.6 | 2 | Site Approval | Admin approves the site | Blocker
17.7 | 2 | Site Approval | LOGIN AS HOST — site now shows "Approved" | Blocker
17.8 | 2 | Site Approval | LOGIN AS GUEST — site now appears on map | Blocker
17.9 | 2 | Site Approval | Admin rejects a different site with reason | Important
17.10 | 2 | Site Approval | Host sees "Rejected" status | Important
18. STRIPE FINANCIAL VERIFICATION (Check Stripe Dashboard)
18.1 | 2 | Stripe | PaymentIntent created with capture_method: manual | Blocker
18.2 | 2 | Stripe | On host approval: PaymentIntent status = succeeded | Blocker
18.3 | 2 | Stripe | On host approval: Charge captured | Blocker
18.4 | 2 | Stripe | 15% application fee deducted | Blocker
18.5 | 2 | Stripe | On host rejection: PaymentIntent cancelled, no charge | Blocker
18.6 | 2 | Stripe | On guest cancel: Payment hold released | Blocker
18.7 | 2 | Stripe | Host Stripe Connect account shows correct balance | Blocker
18.8 | 2 | Stripe | Webhook events received (check Stripe webhook logs) | Important
18.9 | 2 | Stripe | Expired authorizations auto-cancel (runs hourly) | Important
19. CONTACT & SUPPORT
19.1 | 2 | Contact | App: Contact Us form (More → Contact Us) submits | Important
19.2 | 2 | Contact | App: Category dropdown works | Important
19.3 | 2 | Contact | Website: /contact form submits | Important
19.4 | 2 | Contact | Admin sees contact messages in Admin Contact Messages | Important
19.5 | 2 | Contact | Admin can change status (new → read → responded → closed) | Important
20. REFERRAL SYSTEM
20.1 | 2 | Referrals | User can view their referral code | Important
20.2 | 2 | Referrals | Referral code can be copied/shared | Important
20.3 | 2 | Referrals | Signing up with a referral code creates a referral record | Important
20.4 | 2 | Referrals | Referral stats display correctly | Important
20.5 | 2 | Referrals | Website: /dashboard/referrals shows stats + code | Important
21. EDGE CASES & ERROR HANDLING
21.1 | 2 | Edge Cases | No internet: app shows offline mode / graceful error | Important
21.2 | 2 | Edge Cases | Slow internet: loading spinners appear | Important
21.3 | 2 | Edge Cases | Back button behaviour on all screens (no crashes) | Important
21.4 | 2 | Edge Cases | Rotate device: layout doesn't break | Nice-to-have
21.5 | 2 | Edge Cases | Very long text in fields (e.g. 1000-char description) | Nice-to-have
21.6 | 2 | Edge Cases | Special characters in name/description (é, ñ, emoji) | Nice-to-have
21.7 | 2 | Edge Cases | Double-tap "Book" button doesn't create duplicate booking | Blocker
21.8 | 2 | Edge Cases | Double-tap "Pay" doesn't charge twice | Blocker
21.9 | 2 | Edge Cases | Expired token mid-session: auto-refresh or re-login prompt | Blocker
21.10 | 2 | Edge Cases | Booking for a place that becomes full between page load and submit | Important
21.11 | 2 | Edge Cases | Kill app during payment flow — check no orphan payment intents | Important
21.12 | 2 | Edge Cases | Rate limiting: verify blocked after too many password reset attempts | Important
22. VISUAL & UX POLISH
22.1 | 2 | Visual/UX | App cream colour (#ECE8DB) consistent across all screens | Nice-to-have
22.2 | 2 | Visual/UX | App blue colour (#7BA7D8) consistent for buttons/accents | Nice-to-have
22.3 | 2 | Visual/UX | All images load (no broken image placeholders) | Important
22.4 | 2 | Visual/UX | Loading states show spinners (not blank screens) | Important
22.5 | 2 | Visual/UX | Error messages are user-friendly (not raw errors) | Important
22.6 | 2 | Visual/UX | Empty states show helpful messages ("No bookings yet") | Important
22.7 | 2 | Visual/UX | Keyboard doesn't cover input fields | Important
22.8 | 2 | Visual/UX | Scroll works properly on all long screens | Important
22.9 | 2 | Visual/UX | Bottom nav bar icons and labels correct | Important
22.10 | 2 | Visual/UX | App icon and splash screen display correctly | Important
23. SECURITY CHECKS
23.1 | 2 | Security | Accessing someone else's booking returns error (not data) | Blocker
23.2 | 2 | Security | Non-admin accessing admin endpoints returns 403 | Blocker
23.3 | 2 | Security | Non-host accessing host endpoints returns error | Blocker
23.4 | 2 | Security | Expired reset password link doesn't work | Blocker
23.5 | 2 | Security | Can't approve own place (if somehow host = admin) | Important
23.6 | 2 | Security | Review photos strip GPS/EXIF metadata | Important
23.7 | 2 | Security | Password change requires correct current password | Blocker
23.8 | 2 | Security | HTTPS only on all endpoints | Blocker
23.9 | 2 | Security | Tokens stored securely (Keychain/Keystore, not plain text) | Blocker
24. PERFORMANCE
24.1 | 2 | Performance | App cold start time < 5 seconds | Important
24.2 | 2 | Performance | Map panning/zooming is smooth | Important
24.3 | 2 | Performance | Image gallery scrolling is smooth | Important
24.4 | 2 | Performance | Chat messages don't cause memory leak (leave open 5+ mins) | Important
24.5 | 2 | Performance | Website pages load < 3 seconds on 4G | Important
24.6 | 2 | Performance | No console errors on website (check Chrome DevTools) | Important

## Bug Tracker
Bug # | Date Found | Section | Severity | Description | Steps to Reproduce | Expected Result | Actual Result | Status | Fixed In
B1
B2
B3
B4
B5
B6
B7
B8
B9
B10
B11
B12
B13
B14
B15
B16
B17
B18
B19
B20
B21
B22
B23
B24
B25
B26
B27
B28
B29
B30

## Summary
Proper Place — Test Summary
Version | 2.2.0
Test Date
Tester | Pierce Shapton
Platforms | iOS, Android, Web
Backend URL | https://octopus-app-lxh2t.ondigitalocean.app
Website | proper-place.co.uk
Category | Total | Passed | Failed
Blocker (🔴) | 85
Important (🟡) | 100
Nice-to-have (🟢) | 45
TOTAL | 230
Known Issues
1. Production SMTP emails failing from DigitalOcean IPs (relay propagation pending)
2. "host_applications" table may not exist in production DB
SIGN-OFF
Role | Name | Date
Tester
Developer
Release Approved

## Stripe Test Cards
Stripe Test Cards Reference
Card Number | Description | Expiry | CVC | Expected Result
4242 4242 4242 4242 | Successful payment | Any future | Any | Payment succeeds
4000 0000 0000 0002 | Declined card | Any future | Any | Card declined error
4000 0025 0000 3155 | 3D Secure required | Any future | Any | Authentication challenge shown
4000 0000 0000 9995 | Insufficient funds | Any future | Any | Insufficient funds error
4000 0000 0000 0069 | Expired card | Any future | Any | Expired card error
Admin Login
Email: | admin@properplace.com
Password: | AdminPass123!